## 1 — Setup
IO Checkout Tool — Field Test Plan
# | Step | Done? | Notes
Version: 2.0 ¦ Date: 2026-03-20 ¦ Purpose: Set up and validate the IO Checkout Tool at the factory.
# | Step | Done? | Notes
1.1 — Server Setup
Each technician runs the app on their own laptop. Download the release zip and unzip it.
1 | Download the release zip and unzip it to any folder (e.g., C:IOCheckout)
2 | Double-click START.bat
3 | First run: Windows will ask for admin permission (firewall) — click Yes
4 | Wait for the console to show "IO Checkout Tool" with the URL and IP addresses
5 | Note the server IP shown in the console |  | IP:
1.2 — Admin First Login
1 | On any device, open http://<SERVER_IP>:3000
2 | Enter PIN 111111 → log in
3 | You should see the commissioning page (empty, no IOs yet)
1.3 — Change Admin PIN
1 | Click user icon (top-right) → Manage Users
2 | Find "Admin" → click Reset PIN
3 | Enter your new 6-digit PIN → Save
4 | New admin PIN (write it down!) |  | PIN:
1.4 — Create Technician Accounts
1 | Still in Manage Users, enter a technician's full name + 6-digit PIN
2 | Click Create User
3 | Repeat for each technician who will be testing
4 | Users created (list names)
1.5 — Pull IOs from Cloud
1 | Click the PLC button (chip icon in toolbar)
2 | You're on the Cloud Data tab
3 | Enter Subsystem ID |  | ID:
4 | Enter Remote URL |  | URL:
5 | Enter API Password (if required)
6 | Click Pull IOs from Cloud
7 | Wait for "Pulled X IOs" success message |  | IOs pulled:
8 | Close the dialog — IO list should now appear in the table
1.6 — Connect to PLC
1 | Open PLC config again → switch to PLC Connection tab
2 | Enter PLC IP |  | IP:
3 | Enter Communication Path (e.g., 1,0) |  | Path:
4 | Click Connect to PLC
5 | Wait for connection — log shows tag count |  | Tags OK: / Failed:
6 | If tags failed, click Copy Report and save it
7 | Close dialog — PLC icon in toolbar should be green
1.7 — Verify on a Tablet
1 | On a tablet/phone, open http://<SERVER_IP>:3000
2 | Log in with a technician PIN
3 | IO list appears, PLC icon is green
4 | State dots should show current PLC states (green/red circles)
If the tablet can't connect: check same network/Wi-Fi, try STATUS.bat on server to confirm IP, check firewall was accepted.

## 2 — Testing
# | Step | Expected | Pass/Fail | Notes
Test A: Single User Basic Flow
Setup: One device on the same network as the server.
# | Step | Expected | Pass/Fail | Notes
A1 | Press START to begin testing | Button turns red "STOP"
A2 | Physically trigger an input (sensor/switch) | State dot turns green, Pass/Fail dialog appears
A3 | Click Pass | Row turns green, result shows "Passed"
A4 | Trigger another input, click Fail | Asked for failure mode, row turns red
A5 | On a failed IO, click the ? Help button | Diagnostic troubleshooting steps appear |  | ⚠ See note
A6 | Click FIRE on an output IO | Output activates on PLC
A7 | Hold FIRE button, then release | Output stays ON while held, OFF on release
A8 | Use search bar to find a specific IO | Results filter as you type
A9 | Click filter buttons (Pass/Fail/Left/In/Out) | List filters correctly
A10 | Press STOP | Returns to START, no errors
⚠ About the Help (?) button: Work-in-progress feature. Shows troubleshooting steps for specific IO types (beacons, photoeyes, buttons). Only appears for IOs with a tag type assigned — data loads automatically on first login. A dash (—) means no tag type yet.
Test B: Multiple Users (3-5 devices)
Setup: 3-5 devices, each logged in as a different user.
# | Step | Expected | Pass/Fail | Notes
B1 | All devices log in | Each sees IO list with PLC states
B2 | User A presses START | Only User A sees STOP; others still see START
B3 | User B presses START | Both A and B see STOP independently
B4 | Trigger an input | All testing users see the state change
B5 | User A marks Pass on IO #1, User B marks Fail on IO #2 | Each action goes to the correct IO
B6 | User A fires an output | All devices see the output state change
B7 | Two users fire different outputs simultaneously | Both work, no errors
B8 | User A stops testing | Only A goes back to START; B still testing
B9 | Admin pulls new IOs | All devices refresh automatically
B10 | Admin disconnects PLC | All devices show red PLC icon
Test C: Instant Cloud Sync
Setup: Cloud configured and connected. Have cloud dashboard open in another browser.
# | Step | Expected | Pass/Fail | Notes
C1 | Mark an IO as Pass | Result appears on cloud dashboard within 1-2 seconds
C2 | Mark an IO as Fail with comment | Result + comment appear on cloud within 1-2 seconds
C3 | Edit comment on an existing IO | Updated comment syncs to cloud within 1-2 seconds
C4 | Reset an IO result | Cloud shows cleared result within 1-2 seconds
C5 | Disconnect Wi-Fi, mark IO as Pass, reconnect Wi-Fi | Result syncs within 30 seconds of reconnecting
C6 | Mark 5 IOs rapidly (Pass/Fail/Pass/Fail/Pass) | All 5 appear on cloud within a few seconds
C7 | Two users on different laptops test different IOs | Both results appear on cloud independently
Test D: PLC Auto-Reconnect
Setup: PLC connected and testing mode active.
# | Step | Expected | Pass/Fail | Notes
D1 | Unplug PLC Ethernet cable | Toolbar shows amber "Reconnecting" with spinning icon within ~15 seconds
D2 | Wait 30 seconds with PLC unplugged | Icon stays amber, keeps retrying (no crash, no error popup)
D3 | Plug PLC Ethernet cable back in | Toolbar returns to green within 5-10 seconds, tag reading resumes
D4 | Power cycle the PLC (turn off, wait 10s, turn on) | Reconnects automatically after PLC boots — no admin action needed
D5 | While reconnecting, verify IO list still shows | IO list remains visible, previous results intact
D6 | After reconnect, trigger an input | State changes appear, Pass/Fail dialog works normally
D7 | Intentionally click Disconnect in PLC config | Icon turns red, does NOT auto-reconnect (stays disconnected)

## 3 — Remote & Resilience
# | Step | Expected | Pass/Fail | Notes
Part 3: Remote Access via Tailscale
Connect to the server via Tailscale (use the server's Tailscale IP instead of the local IP), then repeat the same tests from Part 2.
# | Step | Expected | Pass/Fail | Notes
C1 | Connect to Tailscale on your device | Connected
C2 | Open http://<TAILSCALE_IP>:3000 | Login page loads
C3 | Repeat tests A1–A8 via Tailscale | Same results as local |  | Note any extra lag
C4 | Repeat tests B1–B3 with one user local + one via Tailscale | Both users see updates
Part 4: Resilience
# | Step | Expected | Pass/Fail | Notes
R1 | Disconnect Wi-Fi for 10 sec, reconnect | App shows "Reconnecting...", then resumes
R2 | Lock tablet screen for 2 min, unlock | App works or auto-reconnects
R3 | Close browser tab, reopen URL | Login page, can resume after login
R4 | (VPN) Disconnect Tailscale, reconnect | App resumes
Part 5: Performance
# | Step | Expected | Pass/Fail | Notes
P1 | Scroll through full IO list (1000+) | Smooth scrolling
P2 | Search/filter with 1000+ IOs | Instant results
P3 | Check server Task Manager while 5 users connected |  |  | Memory: MB CPU: %
Part 6: PLC & Server Resilience
# | Step | Expected | Pass/Fail | Notes
R5 | Power cycle the router (PLC stays on) | PLC reconnects after router boots, testing resumes
R6 | Close server laptop lid for 1 min, reopen | App resumes, PLC reconnects if connection was dropped
R7 | Kill START.bat (Ctrl+C), restart it | App starts fresh, admin reconnects PLC, testing resumes
R8 | Power cycle PLC during active testing with 3+ users | All devices show reconnecting, all resume when PLC returns

## 4 — Issues & Summary
# | Description | Severity | How to reproduce
Issues Found
# | Description | Severity (blocking / annoying / minor) | How to reproduce
1
2
3
4
5
6
7
8
9
10
Summary
| Category | Rating (1-5) | Comments
1 | Setup process
2 | Local network — single user
3 | Local network — multi user
4 | Tailscale VPN (if tested)
5 | Mobile/tablet usability
6 | Overall reliability
Ready for production?
Tester:
Date:
Time spent:
When done: Save this file and send it back. You can also print to PDF from Excel (File → Print → Save as PDF).